## April 9, 2024
Test case plan
2024-04-09
# | Functionality | Scenario | Description | Notes | Tested by | API 34 Pixel 3a | API 31 Pixel 7 Pro | API 31 Pixel 2
1 | Git Configuration | Setup project repository | Set up repository so that all members are able to push/pull via GitHub desktop |  | Sara | Passed | Passed | Passed
2 | Template cleanup | Project contains only necessary starter items | Utilize pre-defined project template in Kotlin, remove redundance xamls, navigation graph, and other functions |  | Sara | Passed | Passed | Passed
3

## April 10, 2024
Test case plan
2024-04-10
# | Functionality | Scenario | Description | Notes | Tested by | API 34 Pixel 3a | API 31 Pixel 7 Pro | API 31 Pixel 2
1 | Verified GitHub repo | Check GitHub setup | Verify the intiial commit and setup of the project is retrievable on GitHub | Using GitHub Desktop client | Andrew, Nader | N/A | N/A | N/A
2 | Updated Gradle | Gradle file includes API dependencies | Verify that information from the Cat API is being retrieved in LogCat |  | Sara | Passed | Passed | Passed
3
4
5

## April 11, 2024
Test case plan
2024-04-11
# | Functionality | Scenario | Description | Notes | Tested by | API 34 Pixel 3a | API 31 Pixel 7 Pro | API 31 Pixel 2
1 | Text View Loading | Description, origin, and temperance loading | Getting respective from the cat API that populates into the text views of the mobile app |  | Nader | Passed | Passed | Passed
2 | JPG images loading | Image loading stub | Getting some images to work by creating a cat API image link header, and appending a cats reference_image_id to the end of the link | Only worked for the file format the link would end in (I ended links with .jpg) See Andrew's image loading test for optimized solution | Sara | Passed | Passed | Passed
3 | All images loading | image loading function | Retrieving all images by fetching url of an image provided by each cat entry in the JSON |  | Andrew | Passed | Passed | Passed